## Export Summary
The Export Summary Page shows how Numbers sheets and tables are converted into Excel worksheets during export. It helps users understand data mapping and ensures easy navigation after conversion.
| Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
| Product Backlog | Table 1 | Product Backlog
| Sprint Backlog | Table 1 | Sprint Backlog
| Stand up Meeting | Table 1 | Stand up Meeting
| Retrospection | Table 1 | Retrospection

## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | As a data engineer, I want to collect and preprocess historical visa application data so that it can be used for predictive modeling. | Must Have | Visa dataset availability | Individual | Completed
Sprint 2 | Sprint 2 | US002 | As a data analyst, I want to perform exploratory data analysis to identify trends in visa processing time across countries and seasons. | Must Have | Cleaned and preprocessed data | Individual | Completed
Sprint 3 | Sprint 3 | US003 | As a machine learning engineer, I want to train and evaluate regression models to predict visa processing time accurately. | Must Have | Feature-engineered dataset | Individual | Completed
Sprint 4 | Sprint 4 | US004 | As a frontend developer, I want to build an interactive dashboard where users can input visa details and view estimated processing time. | Must Have | Prediction API ready | Individual | Completed
Sprint 4 | Sprint 4 | US005 | As a DevOps engineer, I want to deploy and integrate the visa processing time estimator on cloud for demonstration and testing. | Could Have | Backend & frontend integration | Individual | Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US001 | T1 | Collect historical visa application dataset (country, visa type, dates, office) |  |  | Individual | Data Collection | Done | 6 | bar: Day 1 to Day 2
US001 | T2 | Clean dataset, handle missing values, encode categorical variables |  |  | Individual | Data Preprocessing | Done | 10 | bar: Day 2 to Day 4
US002 | T3 | Perform EDA to analyze visa processing time trends and seasonality |  |  | Individual | Data Analysis | Done | 8 | bar: Day 3 to Day 6
US002 | T4 | Feature engineering (seasonal index, country-wise averages) |  |  | Individual | Feature Engineering | Done | 6 | bar: Day 4 to Day 6
US003 | T5 | Train baseline regression model (Linear Regression) |  |  | Individual | Model Training | Done | 6 | bar: Day 5 to Day 8
US003 | T6 | Train advanced model (Random Forest / Gradient Boosting) |  |  | Individual | Model Training | Done | 10 | bar: Day 6 to Day 9
US003 | T7 | Evaluate models using MAE, RMSE and select best model |  |  | Individual | Model Evaluation | Done | 6 | bar: Day 7 to Day 9
US004 | T8 | Develop frontend form for visa details input |  |  | Individual | UI Development | Done | 8 | bar: Day 8 to Day 11
US004 | T9 | Integrate prediction model with frontend interface |  |  | Individual | API Integration | Done | 6 | bar: Day 9 to Day 11
US005 | T10 | Deploy visa processing estimator application to cloud |  |  | Individual | Deployment | Done | 8 | bar: Day 10 to Day 13

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 3 | Incomplete historical visa dataset with missing decision dates | Removed invalid records and applied mean/median imputation
Sprint 2 | Day 2 | High variance in processing time across countries affecting model stability | Introduced country-wise average processing time feature
Sprint 2 | Day 4 | ML model training taking longer due to high feature dimensionality | Reduced features and optimized model parameters
Sprint 3 | Day 3 | Prediction API returning incorrect values due to feature mismatch | Synchronized feature order between training and inference
Sprint 4 | Day 1 | Frontend unable to fetch prediction results due to CORS policy | Enabled CORS in Flask backend and tested API connectivity

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-11-27 | 2025-12-11 | Individual | Document visa data preprocessing steps clearly | Training model without validating raw data | Collaborating during data cleaning | Created shared preprocessing and data dictionary document
2 | Sprint 2 | 2025-12-12 | 2025-12-25 | Individual | Use version control for datasets and model files | Using full dataset without sampling | Validating EDA insights before feature engineering | Implemented dataset & model versioning
3 | Sprint 3 | 2025-12-26 | 2026-01-08 | Individual | Write clear feature definitions and model assumptions | Random hyperparameter tuning | Evaluating models using MAE & RMSE consistently | Finalized optimized Random Forest model
4 | Sprint 4 | 2026-01-09 | 2026-01-22 | Individual | Perform integration testing in parallel | Waiting until final sprint for testing | Regular cross-team sync meetings | Scheduled weekly integration & demo sessions